## Quarterly Yearly Plan
2024 | Quarter Goals | Difficulty 1-3(1 easy and 3 difficult) | Priority Order
Q1 | Initiation process -Product vision and Scope MVPs | 2 | 1
Q2 | MVP 1 :Deploy Basic Flask Web Application in Microsoft Azure Platform | 2 | 2
Q3 | MVP2 : Enchance Web Application by adding MachineLearning components | 3 | 3
Q4 | MVP3: Quality Assurance Testing/Bug fixing | 2 | 4

## Sprint plan
Week | Task | Difficulty 1-3(1 easy and 3 difficult)
2024-01-08 | Project Initiation/Project scope documentation approval | 3
2024-01-15 |  | 1
2024-01-22 |  | 2
2024-01-29 |  | 1
2024-02-05 |  | 3
2024-02-12 |  | 1
2024-02-19 |  | 1
2024-02-26 |  | 3
2024-03-04 |  | 1
2024-03-11 |  | 1
2024-03-18 |  | 2
2024-03-25 |  | 2
2024-04-01 | Setup Github Repository
2024-04-08 | Complete Make file- add commands to install , lint and test and all
2024-04-15 | populate Requirement.txt with all the python libraries needed for the application
2024-04-22 | create project script and test file
2024-04-29 | set up Python enviroment
2024-05-06 | perform local testing
2024-05-13 | Enable GithubActions
2024-05-20 | Set up Azure portal accout
2024-05-27 | Create SSH Keys and add them to Github Repo
2024-06-03 | Connect Github Repo from Azure CLI
2024-06-10 | Perform Connectivity testing between Azure CLI and Github Repo.
2024-06-17
2024-06-24
2024-07-01
2024-07-08
2024-07-15
2024-07-22
2024-07-29
2024-08-05
2024-08-12
2024-08-19
2024-08-26
2024-09-02
2024-09-09
2024-09-16
2024-09-23
2024-09-30
2024-10-07
2024-10-14
2024-10-21
2024-10-28
2024-11-04
2024-11-11
2024-11-18
2024-11-25
2024-12-02
2024-12-09
2024-12-16
2024-12-23
2024-12-30
| Goals | Goals
Q1 | Initiation process -Product vision and Scope MVPs
Q2 | MVP 1 :Deploy Basic Flask Web Application in Microsoft Azure Platform
Q3 | MVP2 : Enchance Web Application by adding MachineLearning components
Q4 | MVP3: Quality Assurance Testing/Bug fixing