## Quarterly Yearly Plan
2024 | Quarter Goals | Difficulty 1-3(1 easy and 3 difficult) | Priority Order
Q1 | Initiation process -Product vision and Scope MVPs | 2 | 1
Q2 | MVP 1 :Deploy Basic Flask Web Application in Microsoft Azure Platform | 2 | 2
Q3 | MVP2 : Enchance Web Application by adding MachineLearning components | 3 | 3
Q4 | MVP3: Quality Assurance Testing/Bug fixing | 2 | 4

## Sprint plan
Week | Task | Program Increment | Sprint | Releases | Features | Points (Estimation of Points) | Difficulty 1-3(1 easy and 3 difficult) | Status
2024-01-08 | Project Initiation/Project scope documentation approval | [5 empty] | 3 | TODO
2024-01-15 | Understanding project | PI 24.1 | Sprint 1 |  |  |  | 1 | TODO
2024-01-22 | Cost analysis | [5 empty] | 2 | TODO
2024-01-29 | Market analysis |  | Sprint 2 |  |  |  | 1 | TODO
2024-02-05 | Benefit Analysis | [5 empty] | 3 | TODO
2024-02-12 | Stakeholders./customer requirements review |  | Sprint 3 |  |  |  | 1 | TODO
2024-02-19 | Feasibility of requirements | [5 empty] | 1 | TODO
2024-02-26 | Finalizing the important features of the product |  | Sprint 4 |  |  |  | 3 | TODO
2024-03-04 | Documentation | [5 empty] | 1 | TODO
2024-03-11 | Review meetings |  | Sprint 5 |  |  |  | 1 | TODO
2024-03-18 | Proposal meetings | [5 empty] | 2 | TODO
2024-03-25 | Scope finialization |  | Sprint 6 | 1 | Project charter deliverable | 8 | 2 | TODO
2024-04-01 | Setup Github Repository | [5 empty] | 3 | TODO
2024-04-08 | Complete Make file- add commands to install , lint and test and all | PI 24.2 | Sprint 1 |  |  |  | 1 | TODO
2024-04-15 | populate Requirement.txt with all the python libraries needed for the application | [5 empty] | 2 | TODO
2024-04-22 | create project script and test file |  | Sprint 2 |  |  |  | 1 | TODO
2024-04-29 | set up Python enviroment | [5 empty] | 3 | TODO
2024-05-06 | perform local testing |  | Sprint 3 |  |  |  | 1 | TODO
2024-05-13 | Enable GithubActions | [5 empty] | 1 | TODO
2024-05-20 | Set up Azure portal accout |  | Sprint 4 |  |  |  | 3 | TODO
2024-05-27 | Create SSH Keys and add them to Github Repo | [5 empty] | 1 | TODO
2024-06-03 | Connect Github Repo from Azure CLI |  | Sprint 5 |  |  |  | 1 | TODO
2024-06-10 | Perform Connectivity testing between Azure CLI and Github Repo. |  |  | 1.2 | MVP 1 :Deploy Basic Flask Web Application in Microsoft Azure Platform | 8 | 2 | TODO
2024-06-17 | Testing and bug fixes |  | Sprint 6 |  |  |  | 2 | TODO
2024-06-24 | finalize initial release and documentation | [5 empty] | 3 | TODO
2024-07-01 | Enhancement requirements | PI 24.3 | Sprint 1 |  |  |  | 1 | TODO
2024-07-08 | UI enhancements use case documentation | [5 empty] | 2 | TODO
2024-07-15 | pipeline enhanements |  | Sprint 2 |  |  |  | 1 | TODO
2024-07-22 | Security features enhancements | [5 empty] | 3 | TODO
2024-07-29 | Build and deployment in Dev |  | Sprint 3 |  |  |  | 1 | TODO
2024-08-05 | Devolopment testing | [5 empty] | 1 | TODO
2024-08-12 | Bug fixes |  | Sprint 4 |  |  |  | 3 | TODO
2024-08-19 | Dev Demo of enhancements to stakeholders | [5 empty] | 1 | TODO
2024-08-26 | Feedback implementation |  | Sprint 5 |  |  |  | 1 | TODO
2024-09-02 | User Acceptance testing |  |  | 2 | MVP2 : Enchance Web Application by adding MachineLearning components | 13 | 2 | TODO
2024-09-09 | User Acceptance testing |  | Sprint 6 |  |  |  | 2 | TODO
2024-09-16 | User Acceptance testing | [5 empty] | 3 | TODO
2024-09-23 | Production delopyment | PI 24.4 | Sprint 1 |  |  |  | 1 | TODO
2024-09-30 | Hypercare documentation | [5 empty] | 2 | TODO
2024-10-07 | Hypercare documentation |  | Sprint 2 |  |  |  | 1 | TODO
2024-10-14 | Data Quality rules creation | [5 empty] | 3 | TODO
2024-10-21 | DDO review of rules |  | Sprint 3 |  |  |  | 1 | TODO
2024-10-28 | Quality assurance dashboard design | [5 empty] | 1 | TODO
2024-11-04 | Design review |  | Sprint 4 |  |  |  | 3 | TODO
2024-11-11 | Design implementation | [5 empty] | 1 | TODO
2024-11-18 | Review and feedback collection |  | Sprint 5 |  |  |  | 1 | TODO
2024-11-25 | Fixes and feedback implemention |  |  | 3 | MVP3: Quality Assurance Testing/Bug fixing | 5 | 2 | TODO
2024-12-02 | Production delopyment |  | Sprint 6 |  |  |  | 2 | TODO
2024-12-09 | Innovation Sprint 1 | [5 empty] | 3 | TODO
2024-12-16 | Innovation Sprint 1 |  | Sprint IP I |  |  |  | 4 | TODO
2024-12-23 | Innovation Sprint 2 | [5 empty] | 3 | TODO
2024-12-30 | Innovation Sprint 2 |  | Sprint IP 2
| Goals | [5 empty] | Goals
Q1 | Initiation process -Product vision and Scope MVPs
Q2 | MVP 1 :Deploy Basic Flask Web Application in Microsoft Azure Platform
Q3 | MVP2 : Enchance Web Application by adding MachineLearning components
Q4 | MVP3: Quality Assurance Testing/Bug fixing