## Quarterly Yearly Plan
2024 | Quarter Goals | Difficulty 1-3(1 easy and 3 difficult) | Priority Order
Q1 | Initiation process -Product vision and Scope MVPs | 2 | 1
Q2 | MVP 1 :Deploy Basic Flask Web Application in Microsoft Azure Platform | 2 | 2
Q3 | MVP2 : Enchance Web Application by adding MachineLearning components | 3 | 3
Q4 | MVP3: Quality Assurance Testing/Bug fixing | 2 | 4

## Sprint plan
Week | Task | Difficulty 1-3(1 easy and 3 difficult)
2024-01-08 | Project Initiation/Project scope documentation approval | 3
2024-01-15 | Setup Github Repository | 1
2024-01-22 | Complete Make file- add commands to install , lint and test and all | 2
2024-01-29 | populate Requirement.txt with all the python libraries needed for the application | 1
2024-02-05 | create project script and test file | 3
2024-02-12 | set up Python enviroment | 1
2024-02-19 | perform local testing | 1
2024-02-26 | Enable GithubActions | 3
2024-03-04 | Set up Azure portal accout | 1
2024-03-11 | Create SSH Keys and add them to Github Repo | 1
2024-03-18 | Connect Github Repo from Azure CLI | 2
2024-03-25 | Perform Connectivity testing between Azure CLI and Github Repo. | 2
| Goals | Goals
MVP 1 :Deploy Basic Flask Web Application in Microsoft Azure Platform